## Sheet1
|  | 18/08/2020 | 25/08/2020 | 2020-01-09 | 2020-08-09 | 18/08/2020 | 18/08/2020 | 18/08/2020 | 18/08/2020
Task | Start Pts | Pts Done Sprint 1.0 | Pts Done Sprint 1.5 | Pts Done Sprint 2.0 | Pts Done Sprint 2.5 | Pts Done Sprint 3.0 | Pts Done Sprint 3.5 | Pts Done Sprint 4.0 | Pts Done Sprint 4.5 | Total Pts Done
Task 1 Design (ERD) Login Feature | 3 | 0 | 1 | 2 | 0 |  |  |  |  | 3
Task 2 Model Login Behaviour | 2 | 0 | 0 | 2 | 0 |  |  |  |  | 2
Task 3 Design Login Page (GUI) | 5 | 0 | 0 | 2 | 2 |  |  |  |  | 4
Task 4 Code Login Page Multiple Users | 8 | 0 | 0 | 2 | 3 |  |  |  |  | 5
Task 5 Code / Create DB connection | 5 | 0 | 0 | 2 | 2 |  |  |  |  | 4
Task 6 Integrate DB with Login Page | 5 | 0 | 0 | 1 | 3 |  |  |  |  | 4
Task 7 Test Login Page | 2 | 0 | 0 | 0 | 1 |  |  |  |  | 1
Task 8 Test Login - Lecturer Secure Login | 3 | 0 | 0 | 0 | 2 |  |  |  |  | 2
Task 9 Test Login - Student Secure Login | 3 | 0 | 0 | 0 | 2 |  |  |  |  | 2
Task 10 Design (ERD) Class Feature | 8 |  |  |  | 2 |  |  |  |  | 2
Task 11 Model Class Behaviour | 3 |  |  |  | 1 |  |  |  |  | 1
Task 12 Design Student Class Page (GUI) | 3 | [8 empty] | 0
Task 13 Code Student Class | 5 | [8 empty] | 0
Task 14 Code / Create Courses | 3 | [8 empty] | 0
Task 15 Test Student Class | 5 | [8 empty] | 0
Task 16 Test Course Creation | 2 | [8 empty] | 0
Task 17 Code / Create Lecturer of Course | 3 | [8 empty] | 0
Task 18 Test Assign Lecturer to Course | 3 | [8 empty] | 0
Task 19 Design DB Migration ?? ERD | 5 | [8 empty] | 0
Task 20 Code Student Data Migration | 5 | [8 empty] | 0
Task 21 Code Add New Student | 3 | [8 empty] | 0
Task 22 Test Student Migration | 2 | [8 empty] | 0
Task 23 Test Add New Student | 2 | [8 empty] | 0
Task 24 Integration Testing (Login + Student Class) | 3 | [8 empty] | 0
Task 25 Code Active Directory / Student Class | 13 | [8 empty] | 0
Task 26 Test Student Class | 5 | [8 empty] | 0
Task 27 Design (ERD) Test Schedule for Class | 3 | [8 empty] | 0
Task 28 Model Test Schedule for Class | 3 | [8 empty] | 0
Task 29 Design Test Schedule GUI | 3 | [8 empty] | 0
Task 30 Code Test Schedule (Create Class) | 5 | [8 empty] | 0
Task 31 Test Create Test Schedule | 2 | [8 empty] | 0
Task 32 Integration Testing (Login + Student Class + Test Schedule) | 8 | [8 empty] | 0
Task 33 Code Test Schedule (Config Time Slots) | 5 | [8 empty] | 0
Task 34 Test Time Slot Configuration - Test Schedule | 2 | [8 empty] | 0
Task 35 Code Test Schedule Student Booking | 3 | [8 empty] | 0
Task 36 Test Student Booking Test Schedule | 1 | [8 empty] | 0
Task 37 Code Test Schedule Delete User function (Lecturer only) | 2 | [8 empty] | 0
Task 38 Test Delete Student Booking | 2 | [8 empty] | 0
Task 39 Design (ERD) Password Reset | 8 | [8 empty] | 0
Task 40 Model Password Reset | 5 | [8 empty] | 0
Task 41 Design Password Reset GUI | 3 | [8 empty] | 0
Task 42 Code Reset PW by Lecturer | 13 | [8 empty] | 0
Task 43 Test Reset PW by Lecturer (other Users) | 2 | [8 empty] | 0
Task 44 Test Reset PW by Lecturer (self) | 2 | [8 empty] | 0
Task 45 Code Reset PW by Student | 5 | [8 empty] | 0
Task 46 Test Reset PW by Student | 5 | [8 empty] | 0
Actual Remaining Effort | 191 | 191 | 190 | 179 | 161 | 161 | 161 | 161 | 161
Estimated Remaining Effort | 191 | 167.125 | 143.25 | 119.375 | 95.5 | 71.625 | 47.75 | 23.875 | 0